## Gantt
FleetPulse — 12-Week Gantt Chart
Project start (Wednesday of Week 1): |  | 2026-10-21 |  | Edit the blue Start week, Duration and Status cells; bars and dates update automatically. Weeks run Wed → Tue.
Phase | Task | Start week | Duration (wks) | End week | Status | W1 Oct 21 | W2 Oct 28 | W3 Nov 4 | W4 Nov 11 | W5 Nov 18 | W6 Nov 25 | W7 Dec 2 | W8 Dec 9 | W9 Dec 16 | W10 Dec 23 | W11 Dec 30 | W12 Jan 6
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Setup & planning | Sensor node EV-01 running in Wokwi | 1 | 1 | 1 | Done
1. Setup & planning | GitHub repo, README, docs | 1 | 1 | 1 | Done
1. Setup & planning | User & expert interviews | 1 | 2 | 2 | In progress
1. Setup & planning | PRD v2 with user insights | 2 | 1 | 2 | Not started
1. Setup & planning | Gantt chart & Kanban board | 2 | 1 | 2 | In progress
1. Setup & planning | Risk register review | 2 | 1 | 2 | Not started
2. Data pipeline | Cloud connection (MQTT) | 3 | 1 | 3 | Not started
2. Data pipeline | 10-asset fleet simulator + fault injection | 4 | 1 | 4 | Not started
2. Data pipeline | Labeled dataset + exploration notebook | 5 | 1 | 5 | Not started
3. Dashboard & model | Dashboard v1 (Streamlit) | 6 | 1 | 6 | Not started
3. Dashboard & model | Anomaly detection: rules vs. Isolation Forest | 7 | 1 | 7 | Not started
3. Dashboard & model | Buffer week (finals) | 8 | 1 | 8 | Not started
3. Dashboard & model | Dashboard v2 + public deployment | 9 | 1 | 9 | Not started
4. Business case | Predictive vs. scheduled maintenance simulation | 10 | 1 | 10 | Not started
4. Business case | Retrospective & case study | 11 | 1 | 11 | Not started
5. Launch | Demo video, final post, resume update | 12 | 1 | 12 | Not started
Ongoing | Weekly status update (every Tuesday) | 1 | 12 | 12 | In progress
LinkedIn | ◆ Kickoff post | 1 | 1 | 1 | Done
LinkedIn | ◆ Research post (1960 paper) | 1 | 1 | 1 | Done
LinkedIn | ◆ Feedback poll | 2 | 1 | 2 | In progress
LinkedIn | ◆ Post 2: the PM side | 4 | 1 | 4 | Not started
LinkedIn | ◆ Post 3: first data | 6 | 1 | 6 | Not started
LinkedIn | ◆ Post 4: dashboard demo | 9 | 1 | 9 | Not started
LinkedIn | ◆ Post 5: business case | 11 | 1 | 11 | Not started
LinkedIn | ◆ Post 6: wrap-up | 12 | 1 | 12 | Not started
Progress summary
Tasks done | 2
Tasks in progress | 3
Total tasks | 17
% tasks done | 11.76%
Legend:
Done
In progress
Planned
◆ = milestone (LinkedIn post). Blue text = editable inputs. Source: FleetPulse 12-week plan (PRD).